## Sheet1
Week | Phase | Tasks | Tools / Tech Stack
1–2 | Planning & Requirement Analysis | Define scope of the platform; Finalize dataset (Citizen Feedback Data); Decide on modules (Data Ingestion, NLP, Dashboards); Identify key analytics outcomes (e.g., sentiment score, trending concerns) | Google Docs, Draw.io, Trello
3–4 | System Design & Architecture | Design high-level architecture & data flow; Finalize database/storage structure; Create UI wireframes for dashboard; Draft schema for storing processed feedback | Streamlit, Draw.io
5–6 | Data Collection & Integration | and parse TSV/CSV data; Extract relevant fields (review text, rating, category); Store in DB or Pandas DataFrames | Python, Pandas
7–8 | Analytics & ML Modeling | Data Analytics, EDA and Preprocess text (cleaning, tokenizing, stopword removal); Train sentiment classifier (Logistic/SVM); Optional: Topic modeling with LDA or BERTopic; Test accuracy on review data | scikit-learn, spaCy, Gensim, Transformers
9–10 | Dashboard Development | Build Streamlit app to show: Category-wise sentiment trend, Top complaints/topics, Ratings histogram; Include filters by product, rating, date | Streamlit, Plotly, Matplotlib, Seaborn
11–12 | Testing, Optimization & Reporting | Refactor pipeline; Add report download/export features (PDF/Excel); Validate insights visually; Gather feedback for UI/UX; Finalize project documentation | Streamlit, fpdf/reportlab, pandas-to-excel